## Sheet1
RISK MATRICES | For Project JUICEE
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | VERY HIGH
Very Likely | Low medium | Medium | Medium high | High | SUPER HIGH
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
RSI | My wrists could be aching | Ensure I move wrists about . Remember to use the new mouse with the ball. | To keep my wrists safe for the future | Very Unlikely | Minor | Low
Losing my Work | Loss of work will affect the entire Project and Will lead to regression in progress. | Ensure I continouly save my work and ensure it is present. | to keep all work securly saved in multiple places by pushing work regularly to GitHub after completion. Also back-up LOCALLY and REMOTELY | Very Unlikely | Catastrophic | Medium
Injury | Involvement in activity could lead to injury during project and become incapable of finishing project | Ensure i Excercise responsiberly and rest well. | be cautious when excerising to prevent injury and eat a balanced diet to decrease recovery time if injured. | Unlikely | Major | Low medium
Computer Malfunctioning | If Computer malfunctions it will mean I can’t use It any more to do the project. | ensure i check my computer health regularly | Monitor computer health and reduce the usage of CPU intensive applications whilst working on Project critical Tasks. WORK Laptop = ONLY FOR WORK! | Very Unlikely | Hazardous | Medium
GitHub Servers being down | I would then be unable to access the remote work to enhance development | Ensure my I regulalry check github status. | ensure my remote repository is upto date with my github repository at all times. | Very Unlikely | Catastrophic | Medium
Mentor is not present | Mentor not available for support due to illness Or being occupied with others from the cohort | be patient until he is avaible to help me and do other work and come back to that particular task | use resources on Qa Community - w3school & cloudacademy + ofc Google | Moderate | Minor | Low Medium
Bad Internet / No Internet | Loss of internet preventing access to GitHub And not being able to reach my cohort on Teams | Ensure i have a strong internet Provider. Currently Preapring for a move over n the 25th to SECURE a CONSTANT UNNBREAKABLE INTERNET from Vodafone. Had enough of dropped packets. | Ensure that the RJ45 Lead is a tested cable after making it yourself to be sure (10/10) SOD wifi - Use my phone hotspot if internet goes down. | Unlikely | Hazardous | Medium
ISP Change Over | ISP Provider SWAP Expected downtime during SETUP & phone number tranfer. Use HotSpot for 1 day to prevent loss of connection. | Ensure i have a strong internet Provider. Currently Preapring for a move over on the 25th to SECURE a CONSTANT UNNBREAKABLE INTERNET from Vodafone. Had enough of dropped packets. Dates have moved - check dates. | Ensure that the RJ45 Lead is a tested cable after making it yourself to be sure (10/10) SOD wifi - Use my phone hotspot if internet goes down. | Unlikely | Hazardous | Medium
Problems in Merging between two branches | Could happen due to incorrect branching workflow Which will lead to merge conflicts during feature merging. | Ensure i know what branch i am working on and the changes i've made to it. DOUBLE CHECK -- CD in - LS -AL old school linux we know this | keep track of the feature-branch workflow and ensure to branch off develop branch to follow branching best practises and that the branches have a shared history. | Moderate | Minor | Low Medium
Customer Changes Their Mind | Frequently happens due to human nature | Ensure we have their wants and needs covered. We WILL make vaious choices for their pallette. | KNOW what he customer wants...the variation will be hte Users databse for private access and control of their CMS. | Moderate | Minor | Low Medium
Follow the directions | Do not diviate | We are apt to | keep checking your work - may help here | Very Unlikely | Minor | Medium